## Product Backlog
Product Name: | Exceptional Laptops and Supercomputers Always (ELSA) | [6 empty] | Complete Fields in Green!!!
Team ID:
| Team Member Name | [5 empty] | Initials | Student ID
Required | ALISHA KUNWAR | [5 empty] | AK | 1001668106
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 22 |  |  |  | Total | Total number of features (in column H)
1 | 21 | 1 |  |  | 1 | Total features left at the end of Sprint #1
2 | 17 | 4 |  |  | 2 | Total features left at the end of Sprint #2
3 | 17 | 0 |  |  | 3 | ...and so on
4 | 17 | 0
5 | 17 | 0
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 2 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly
OPT | 2 | 1 |  | 8 |  | Finished in Sprint 2 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product
DESKT | 3 | 1 |  | 8 |  | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 13 |  | Finished in Sprint 2 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what
WIN | 5 | 2 |  | 21 |  | Finished in Sprint 2 | Sales Staff | Replace text interface with GUI main window | Use it more easily | Recommend baselining Nim from Lecture 13
OUTM | 6 | 2 |  | 5 |  |  | Sales Staff | Replace list of data records with main window list | Access the data directly in the window | Try using std::ostringstream to capture operator<< formatting
INDIA | 7 | 2 |  | 8 |  |  | Sales Staff | Replace data queries with series of dialogs | Do everything within the GUI | Recommend baselining EntryDialog from Lecture 14
ABOUT | 8 | 2 |  | 1 |  |  | Director | Provide About dialog for documenting licenses | Avoid a lawsuit
SAVE | 9 | 3 |  | 13 |  |  | Manager | Save the data to a default file (File > Save) | Persist our data through the years | This requires modifying the “model” to save and reload each object from a provided stream
SAVAS | 10 | 3 |  | 5 |  |  | Manager | Save the data to a specified file (File > Save As) | Persist our data through the years | Use Gtk::FileChooser
LOAD | 11 | 3 |  | 8 |  |  | Manager | Load the data from a specified file (File > Open) | Persist our data through the years | Use Gtk::FileChooser
QRAM | 12 | 4 |  | 21 |  |  | Customer | Store and display additional RAM data | Ensure I purchase the correct product
DCUST | 13 | 4 |  | 8 |  |  | Sales Staff | Replace Insert Customer dialogs with single dialog | Enter data more quickly
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
QCPU | 14 |  | 25 | 13 |  |  | Customer | Store and display additional CPU data | Ensure I purchase the correct product | Derive classes from Options and call operator<< polymorphically
QDISK | 15 |  | 10 | 5 |  |  | Customer | Store and display additional Disk data | Ensure I purchase the correct product
DORD | 16 |  | 15 | 8 |  |  | Sales Staff | Replace Insert Order dialogs with single dialog | Enter data more quickly
DOPT | 17 |  | 40 | 21 |  |  | Sales Staff | Replace Insert Option dialogs with single dialog | Enter data more quickly
DDESK | 18 |  | 25 | 13 |  |  | Sales Staff | Replace Insert Desktop dialogs with single dialog | Enter data more quickly
TBAR | 19 |  | 10 | 5 |  |  | Customer | Access key functionality with a toolbar AND menu | More quickly access the behaviors I need | You can baseline this code from Nim’s Mainwin::Mainwin as well
SCROL | 20 |  | 10 | 5 |  |  | Customer | Make the main window’s data area scrollable | See large volumes of data | The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
DEPR | 21 |  | 25 | 13 |  |  | Inventory | Deprecate a product | Avoid selling products that are out of production | This requires a Boolean with getter and setter in the Options and Desktop classes to indicate which are deprecated. The index number may pose interesting challenges, since deprecation will create gaps.
SBAR | 22 |  | 15 | 8 |  |  | Manager | Replace the Gtk::Label for the status bar with Gtk::Statusbar, and maintain a message stack | Better track status of messages | Just swapping Gtk::Statusbar for Gtk::Label is trivial. Think through how to manage a first-in last-out stack of messages

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2020-03-03 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-24
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 16 | 0
Day 2 Left | 16 | 0
Day 3 Left | 14 | 2
Day 4 Left | 13 | 1
Day 5 Left | 7 | 6
Day 6 Left | 3 | 4
Day 7 Left | 0 | 3
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST |  | Write the Customer class | Completed Day 5 | Test each class and method as it is written
2 | CUST |  | Write operator<< for Customer | Completed Day 5 | Commit and push AT LEAST once every class or update
3 | CUST |  | Write Store::add_customer, num_customers, and customer | Completed Day 5 | You are free to determine your own algorithm for mapping the (now) 21 days of this sprint to the 7 reporting days – e.g., 1/3 days, the first 7 days you actually do work, etc.
4 | OPT |  | Write the Options class sans to_string | Completed Day 3
5 | OPT |  | Write Options::to_string and its operator<< | Completed Day 3
6 | OPT |  | Write Store::add_option (to Store), num_options, and option | Completed Day 4
7 | DESKT |  | Write the Desktop class with add_option method | Completed Day 5
8 | DESKT |  | Write the Desktop::price method | Completed Day 5
9 | DESKT |  | Write operator<< for Desktop | Completed Day 5
10 | DESKT |  | Write Store::new_desktop, add_option (to desktop), num_desktops, and desktop | Completed Day 6
11 | ORDER |  | Write the Order associative class and constructor | Completed Day 6
12 | ORDER |  | Write Order::add_product | Completed Day 6
13 | ORDER |  | Write Order::price | Completed Day 6
14 | ORDER |  | Write Store::new_order, add_desktop, num_orders, and order | Completed Day 7
15 | ORDER |  | Integrate and test with cse1325_prof/elsa/sprint_1/main.cpp | Completed Day 7
16 | ORDER |  | Ensure ALL CODE is on GitHub by deadline! | Completed Day 7
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2020-03-24 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-31
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 13 | 3
Day 2 Left | 10 | 3
Day 3 Left | 8 | 2
Day 4 Left | 6 | 2
Day 5 Left | 4 | 2
Day 6 Left | 1 | 3
Day 7 Left | 0 | 1
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST |  | Slightly changes on Store class | Completed Day 1
2 | ORDER |  | Slightly changes on Order class | Completed Day 1
3 | WIN |  | Create File and View Tab on entry dialog | Completed Day 1
4 | ABOUT |  | Create Insert and Help Tab on entry dialog | Completed Day 2
5 | OPT |  | Write Mainwin::on_view_peripheral_click | Completed Day 2
6 | CUST |  | Write Mainwin::on_view_customer_click | Completed Day 2
7 | DESKT |  | Write Mainwin::on_view_desktop_click | Completed Day 3
8 | ORDER |  | Write Mainwin::on_view_order_click | Completed Day 3
9 | CUST |  | Write Mainwin::on_insert_customer_click | Completed Day 4
10 | OPT |  | Write Mainwin::on_insert_peripheral_click | Completed Day 4
11 | DESKT |  | Write Mainwin::on_insert_desktop_click | Completed Day 5
12 | DESKT |  | Write Mainwin::on_insert_order_click | Completed Day 5
13 | DCUST |  | Modify entrydialog file | Completed Day 6
14 | WIN |  | Modify main.cpp | Completed Day 6
15 | LOAD |  | Integrate and test | Completed Day 6
16 | OUTM |  | ensure all code is on github | Completed Day 7
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2020-03-31 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-07
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2020-04-14 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-28
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint |  | You are free to determine your own algorithm for mapping the (now) 21 days of this sprint to the 7 reporting days – e.g., 1/3 days, the first 7 days you actually do work, etc.
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84